## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2175-swen-261-04-b
Testing Team Name

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | CV 3/4/18
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | CV 3/4/18
| Given that no one else is using my name when I enter my name containing only alphanumeric characters or spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | CV 3/4/18
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the Signin form for me to try another name. | Pass | CV 3/4/18
| Given that I am on the Signin page when I enter a name that contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Signin form. | Pass | CV 3/4/18
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | CV 3/4/18
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | CV 3/4/18
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | CV 3/4/18
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | CV 3/4/18
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | CV 3/4/18
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | CV 3/4/18
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | CV 3/4/18
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | CV 3/4/18
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | CV 3/4/18
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | CV 3/4/18
As an AI I want to move checkers so that the game can be played.
As an AI I want to take positions so that I can win.
As an AI I want to Learn from mistakes so that I can win every game.
As an easy AI I want to make jokes for the user to entertain the player
As a Player I want to drag one of my pieces to a new location on the board so that I can make progress in the game.
As a Player I want to get feedback when I drag a piece so that I know where I am allowed to put it down.
As a Player I want the application to tell me why I can’t make a move so that I don’t get confused about what I can and can’t do.
As a Player I want to be informed when I am required to make a move so that I don’t try to make a different move than I need to.
As a Player I want to have visual feedback so that I know which pieces I am allowed to move this turn.
As a Player I want to control the speed of playback of a game so that I can slow it down and look carefully or go quickly through and get the basic idea of the game.
As a Player I want to choose a game from my list of saved games so that I can review the game and moves.
As a Player I want to see the replayed game in a similar setting to where it was played originally so that I can easily track the movements and game status.
As a Player watching a game, I want to be told the names of each player in the game so that I know who I am watching.
As a Player I want to pause and resume watching a replay game so that I can stop to analyze a position or practice my own playing.
As a Player I want to see if it is my turn or not so that I know when I can move.
As a Player I want to see a count of the remaining pieces so that I can evaluate my progress in the game.
As a Player I want to resign the game so that I can end it without playing to completion.
As a Player I want to view the games which I have saved so that I can choose which one to watch.
As a Player I want to decide, at the end of a game, to save it so that I can review it at a later date.
As a Player I want to delete a game I have saved so that it does not clutter up my list of saved games.
As a Player I want to choose another player so that I can challenge them to a game of checkers.
As a Player I want to see the pieces both my opponent and I have captured so that I can evaluate my progress in the game.
As a Player I want to see the checkers board so that I can know where the pieces currently in play are placed and what kind of piece they are.