## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2175-swen-261-04-b
Testing Team Name

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | CV 3/4/18 | Untested | was not tested
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | CV 3/4/18 | Untested | was not tested
| Given that no one else is using my name when I enter my name containing only alphanumeric characters or spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | CV 3/4/18 | Untested | was not tested
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the Signin form for me to try another name. | Pass | CV 3/4/18 | Untested | was not tested
| Given that I am on the Signin page when I enter a name that contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Signin form. | Pass | CV 3/4/18 | Untested | was not tested
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | CV 3/4/18 | Untested | was not tested
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | CV 3/4/18 | Untested | was not tested
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | CV 3/4/18 | Untested | was not tested
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | CV 3/4/18 | Untested | was not tested
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | CV 3/4/18 | Untested | was not tested
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | CV 3/4/18 | Untested | was not tested
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | CV 3/4/18 | Untested | was not tested
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | CV 3/4/18 | Untested | was not tested
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | CV 3/4/18 | Untested | was not tested
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | CV 3/4/18 | Untested | was not tested
---SPRINT 2---
Epic: Piece Movement
As a Player I want to drag one of my pieces to a new location on the board so that I can make progress in the game. | Given that I am playing a game when I start to drag a checkers piece then I pick it up and start moving it. |  |  | Pass | CV;4/2/18
| Given that I am holding a piece over a valid location when I let go of the piece then it moves to the new space I held it over. |  |  | Untested
| Given that I am holding a piece over an invalid location when I drop it then it moves back to where it was before I picked it up. |  |  | Untested | was not tested
| Given that I have dropped a piece when I try to move a different piece then I am not allowed to pick it up. |  |  | Untested | was not tested
| Given that I have moved a non-king piece to the opponent's edge of the board when I have made the move then that piece becomes a king piece. |  |  | Untested | was not tested
As a Player I want to get feedback when I drag a piece so that I know where I am allowed to put it down. | Given I am holding a piece when I hover over a space on the checkerboard then I see a visual indication of whether I am allowed to drop the piece in that location. |  |  | Untested | was not tested
| Given I am holding a piece over an invalid location when I drop the piece then the piece does not drop where I held it over. |  |  | Untested | was not tested
| Given that the piece I am trying to move is a king when I try to move it backwards then I am allowed to. |  |  | Untested | was not tested
| Given that the piece I am trying to move is not a king when I try to move it backwards then I am not allowed to. |  |  | Untested | was not tested
As a Player I want to capture the other player's pieces so that I can progress in the game. | Given I have made a move over an opponent's piece when I submit my turn then their piece is captured and removed from the board. |  |  | Untested | was not tested
| Given I have not submitted my turn and have made a jump move when I try to make another jump move then I am allowed to jump again. |  |  | Untested | was not tested
As a Player I want to be informed when I am required to make a move so that I don’t try to make a different move than I need to. | Given I have at least one jump move available to me when it is my turn then I am only allowed to make one of the jump moves. |  |  | Untested | was not tested
Epic: Game State
As a Player I want to know when the game is over so that I don't try to continue playing. | Given I am playing a checkers game when a player makes a move which causes the game to be over then I see a message that the game is over and who won. |  |  | Pass | acr;4/2/18
| Given the checkers game has ended when I return to the home screen then another player is able to challenge me to another game. |  |  | Pass | acr;4/2/18
Epic: Resignation
As a Player I want to resign the game so that I can end it without playing to completion. | Given that it is my turn and I have not moved any pieces when I click the resign button then the game is ended and I am shown the game over screen. |  |  | Pass | acr;4/2/18
| Given that I am playing a game when the other player resigns then I am told that they have resigned and the game is over. |  |  | Pass | acr;4/2/18
| Given that I have made a move when I try to click on the resign button then I am prevented from doing so. |  |  | Untested | was not tested
Epic: Save Management
As a Player I want to view the games which I have saved so that I can choose which one to watch. | Given that I am signed in when I view the home page then I see a link to manage my saved games. |  |  | Pass | acr;4/2/18
| Given that I am signed in when I navigate to the saved games page then I see a list of the games which I have saved. |  |  | Pass | acr;4/2/18
| Given that I am in the saved games page when I click on a saved game then I am shown a replay of that game. |  |  | Untested | was not tested
As a Player I want to decide, at the end of a game, to save it so that I can review it at a later date. | Given that I am on the Game page when my current game has ended then I see an option to save the game to my account's saved games. |  |  | Untested | was not tested
| Given that the game has ended when neither player has chosen to save it then the game record is discarded. |  |  | Pass | acr;4/2/18
As a Player I want to delete a game I have saved so that it does not clutter up my list of saved games. | Given I am logged in when I navigate to the save management page then I see an option to delete one of the saved games. |  |  | Pass | acr;4/2/18
| Given I am on the save management page when I choose to delete a game then it is removed from my list of saved games. |  |  | Pass | acr;4/2/18
---SPRINT 3---
Epic: Artificial Intelligence
As an AI I want to move checkers so that the game can be played. | Given it is the Ai's turn when there is a move available then I expect the ai to move.
Given it is the AI's turn when there is both a piece to take over and movement is available then I expect the Ai to take the piece and ignore the move.
As an AI I want to take positions so that I can win. | Given there is an option to take over a piece when it is the ai's turn then I expect the ai to take that piece.
As an AI I want to Learn from mistakes so that I can win every game. | Given the ai has just taken its turn when the ai has made a move or taken over a piece then I expect a matrix of all the game data to be cached.
Given the ai has won when the game ends then I expect the cached data to be saved.
As an easy AI I want to make jokes so that the player is entertained. | Given the ai has a move when it is the ai's turn then I expect the ai to make a random move
Given it is the ai's turn when the ai goes to make a move then I expect the ai to move the players piece by "mistake"
As a Player I want to choose an AI so that I can play a game of checkers against it. | Given the home screen is open when the player is selecting a game then I expect the option to open a game with an ai
given that the player has selected a game with an ai when the game opens then I expect the ai to be a new instance of the ai.
Epic: Watching a Saved Game
As a Player I want to see the replayed game in a similar setting to where it was played originally so that I can easily track the movements and game status. | Given I have decided to review a saved game when I choose it from my saved games list then I see the game presented in a similar interface to the gameplay interface.
Given I am watching a game when there are moves which have not been made yet then I see the next move in the sequence made.
As a Player I want to pause and resume watching a replay game so that I can stop to analyze a position or practice my own playing. | Given I am on the game replay page when I am watching a game then I see options to play and pause the replay.
Given I am watching a replay when I click the pause button then moves stop playing back.
Given I am watching a replay which is paused when I click the play button then the game replay resumes moving pieces.
As a Player I want to control the speed of playback of a game so that I can slow it down and look carefully or go quickly through and get the basic idea of the game. | Given I am watching a game replay when the replay is active then I see options to change the speed at which moves occur in sequence.
Given I am watching a replay when I choose to make it play more quickly then the moves occur more rapidly after one another.
Given I am watching a replay when I choose to make it play more slowly then the moves occur with more time in between each one.
As a Player watching a game, I want to be told the names of each player in the game so that I know who I am watching. | Given I am watching a game replay when I look at the user information section then I see which player's turn it is as well as the players' names.